## May 2026
Sr. No. | Task | Task type | Status
2026-05-01
1 | I worked on completing all three IGRS data flows—database/SDK connection, CSV upload, and JSON/PDF OCR processing—and ensured they are functioning correctly. The mutation workflow is also working properly, and verification is successful when fetching data from the database (PDF upload-based verification still needs further work). | IGRS End-to-End Flow Integration & Verification | Completed
2026-05-04
1 | Today i have go to Krushi University | Demo | Completed
2026-05-05
1 | I worked on a solution to split merged PDF pages accurately into structured folders in JustifAI 0.2. After that, I reviewed the bug sheet, fixed the identified issues, and pushed the updates to the repository. | PDF Split Optimization & Bug Fixes (JustifAI 0.2) | Completed
2026-05-06
1 | Today i have go to RMC | Demo | Completed
2026-05-07
1 | I worked on the Birth Certificate module and deployed the new IGRS live version on Render. I also conducted research related to the eNagar system to understand its workflow and possible integration approaches. | Birth Certificate Module, IGRS Deployment & eNagar Research | Completed
2026-05-08
1 | I completed the Hyperledger integration for JustifAI and ensured the required functionality and connectivity are working properly within the system. | JustifAI Hyperledger Integration | Completed
2026-05-11
1 | I worked on the SMP project and fixed grade promotion bugs. After that, I created the SMP PPT content document. I also worked on some JustifAI-related tasks, including improving the landing page UI and adding logo animations. | SMP Bug Fixing & PPT Documentation JustifAI Landing Page UI & Logo Animation Development | Completed
2026-05-12
1 | I worked on successful deployment of the JustifAI Hyperledger setup, including both backend and frontend integration. After that, I fixed some frontend issues for handover to Bhadresh Bhai and deployed the live codebase chain code. | JustifAI Hyperledger Deployment & Integration | Completed
2026-05-13
1 | I worked on the supply chain project and developed a one-stage MVP based on the research findings. I added new workflow improvements and implemented a structured QR-based supply chain flow for better tracking and verification. | Supply Chain MVP Development & QR Workflow Enhancement | Completed
2026-05-14
1 | I worked on the JustifAI Hyperledger integration and added logging and audit log functionality for better tracking and monitoring. I also conducted R&D on training PDF data and explored possible solutions for improving document processing and handling. | JustifAI Hyperledger Enhancement & PDF Data Research | Completed, R&D Done
2026-05-15
1 | I worked on the Hyperledger email functionality and continued development on the template function module. The template functionality is still under progress, and I am actively working on fixing and improving it for proper performance and integration. | Hyperledger Email & Template Function Enhancement | Process
2026-05-16
1 | Today I have worked on creating a daily task share feature for the automation Telegram bot. | Daily Task Automation | Completed

## April 2026
Sr. No. | Task | Task type | Status
2026-04-01
1 | I worked on resolving backend issues in the PortChain system and handled infrastructure-related tasks to improve system stability and performance. | PortChain Backend Issue Resolution & Infrastructure Work | Completed
2026-04-02
1 | I worked on the PortChain frontend and contributed to solving some parts of the SMP system. I also made progress on application development to support overall system functionality. | PortChain Frontend, SMP Solution & App Development | Completed
2026-04-03
1 | I worked on both the backend and frontend of the QCI system. I also designed and analyzed the blockchain architecture using Hyperledger to ensure proper integration and scalability. | QCI Development & Hyperledger Architecture Design | Completed
2026-04-06
1 | I worked on integrating PortChain APIs and ensured proper communication between different system components for smooth functionality. | PortChain API Integration | Half Completed
2026-04-07
1 | I worked on fixing backend bugs in the JadeLC system and resolved OCR-related issues to improve accuracy and system reliability. | JadeLC Backend Bug Fixes & OCR Issue Resolution | Completed
2026-04-08
1 | I worked on modifying the Hyperledger setup in Justifai. I explored how these changes can be implemented, identified the key parameters involved, and discussed the approach with Bhadresh Bhai | Justifai Chnage Layout and Stcture | Completed
2026-04-09
1 | I worked on the SMP app and web backend, focusing on student promotion updates. | Student Promotion SMP | Completed
2026-04-10
1 | I visited Junagadh with Rohan Sir to deliver a demo of Justifai and IGRS. | Client Demo / Presentation | Completed
2026-04-13
1 | I worked on research related to reference modules (Sunday work), explored how modules function, and studied basics of Quantum Computing. I also practiced improving vocabulary as suggested by Rohan Sir, and worked on Justifai OCR. | Research & Development, Learning, OCR Implementation | Completed
2026-04-14
1 | I attended a session at JG University where they decided to go live and share a template. I created the template accordingly. I also identified and worked on resolving a promotion-related issue, though some parts are still pending. Additionally, I made changes in the SMP app to fix UI issues occurring on different devices. | Development, Bug Fixing, UI Optimization | Completed
2026-04-15
1 | I worked on improving both the JustifAI and IGRS systems to make them more stable, accurate, and properly aligned with the required functionality. | JustifAI & IGRS System Enhancement | Completed
2026-04-16
1 | I attended a meeting with Krushi University and presented a demo of JustifAI. During the session, they shared their result and degree data for further processing and integration. | Krushi University Meeting & JustifAI Demo | Completed
2026-04-17
1 | I worked on implementing a new upload flow in Justifai 0.2 for Krushi University marksheets and degree certificates, ensuring a smoother and more structured process for document handling and verification. | Justifai 0.2 – Marksheet & Degree Upload Flow | Completed
2026-04-20
1 | In the first half of the day, I went to my college. In the second half, I worked on running the OCR implementation and improved the canonicalization process to ensure more accurate and consistent data handling. | OCR Implementation & Canonicalization Enhancement | Completed
2026-04-21
1 | I completed the marksheet implementation and started working on transcript OCR along with Bhadresh and Soumyjit to improve data extraction and processing. | Marksheet Completion & Transcript OCR Development | Completed
2026-04-22
1 | I worked on preparing the JustifAI demo for CHARUSAT University. I also attempted to fix existing issues in the system, but they are not fully resolved yet and require further debugging. | CHARUSAT Demo Preparation & Issue Debugging | Completed
2026-04-23
1 | I worked on adding canonicalization and integrating OCR spacing improvements in JustifAI. However, the OCR results are not working as expected and require further refinement and debugging. | Canonicalization & OCR Integration Testing | Completed
2026-04-24
1 | I finalized the canonicalization implementation and pushed the updated code. I worked on resolving the main OCR extraction issues and completed the related improvements. I also developed the SDK for integration. In addition, I conducted research on blockchain, quantum concepts, and machine learning to explore ways to further improve the system. | Canonicalization Finalization, OCR Fixes, SDK Development & Blockchain Research | Completed
2026-04-27
1 | I worked on the JustifAI SDK and tested the connection between the ERP and SDK to ensure proper integration. I also implemented a scanned document crop function in the SMP scanner to improve document processing and accuracy. | JustifAI SDK Development, ERP Integration Testing & SMP Scanner Enhancement | Completed
2026-04-28
1 | I improved the revocation functionality in JustifAI and reviewed the STL documentation. I also tested JustifAI 0.2—marksheet and degree processing are working well, while transcript data still has some issues that I am checking. Additionally, I finalized and implemented the JustifAI 0.2 workflow for the system. | Revocation Enhancement, JustifAI 0.2 Testing & Flow Implementation | Completed
2026-04-29
1 | I supported JustifAI testing with Meetali Ma’am. After that, I reviewed IGRS documents to assess how many are production-ready. I also conducted research on smart route optimization using quantum theorem–based logic to explore potential improvements in system efficiency. | JustifAI Testing Support, IGRS Readiness Review & Optimization Research | Completed
2026-04-30
1 | I worked on implementing bulk CSV data upload in the IGRS system and ensured the complete authority approval process is handled correctly across all stages. | IGRS Bulk CSV Upload & Authority Approval Workflow | Completed

## March 2026
Sr. No. | Task | Task type | Status
2026-03-02
1 | we implemented multi-language support in certificates and added the student wallet integration. We also made improvements to the OCR system, enhanced multi-QR detection, and optimized processing time to reduce overall time consumption. In addition, we performed load testing on Justifai with 2000 certificates to validate performance and system stability. | Multi-Language Certificates, Student Wallet & Performance Optimization | Completed
2026-03-03
1 | In the first half of the day, we conducted a demo for Gujarat University and presented the system workflow and features. In the second half, we worked on Jantri development, focusing on implementation and system improvements. | GU University Demo & Jantri Development | Completed
2026-03-05
1 | we worked on the IGRS mutation module, including creating the mutation tree structure. We also worked on e-stamp integration and performed data entry for Jantri and Gujarat-related datasets. | IGRS Mutation System & Data Entry Development | Completed
2026-03-06
1 | we worked on the IGRS frontend and improved the mutation system to properly handle different land transaction scenarios, including buy and sell cases, ensuring the workflow works accurately for all situations. | IGRS Frontend Development & Mutation System Enhancement | Completed
2026-03-09
1 | we worked on the IGRS system and enhanced the mutation logic to allow the same person to be added again for the same land when required by the mutation process. This ensures the workflow supports all valid land ownership scenarios | IGRS Mutation Logic Enhancement | Completed
2026-03-10
1 | I presented the IGRS system demo in Gandhinagar. After that, we discussed and planned a crypto trading platform, but the idea was not finalized and the plan was dropped. Later, I conducted research on possible areas within the Labour Department where blockchain technology could be implemented. | IGRS Demo, Crypto Platform Planning & Blockchain Research | Completed
2026-03-11
1 | I traveled from Ahmedabad to Jalgaon to present the JustifAI system demo along with Yogesh Sir and Rohan Sir. The session focused on demonstrating the platform features and overall workflow. | JustifAI Demo Presentation & Travel | Completed
2026-03-12
1 | we returned from Jalgaon to Ahmedabad after completing the meeting with Jalgaon University and the related discussions regarding the system. | Travel & Meeting Follow-up – Jalgaon University | Completed
2026-03-13
1 | at 11 AM, I went to the airport to travel to Bangalore to attend the TokenIQ event. | Travel for TokenIQ Event | Completed
2026-03-14
1 | I attended the TokenIQ event along with Mandeep and Jatin Sir. During the event, I learned about how crypto trading platforms work, how traders operate in the crypto market, and how market dynamics function. After 2 PM, I also explored concepts related to Web2, Web3, and how blockchain technology is used in the crypto ecosystem. Additionally, we participated in some fun activities at the event and won goodies. | TokenIQ Event Participation & Crypto Market Learning | Completed
2026-03-15
1 | Mandeep, Jatin Sir, and I attended a session by CA Manish where we learned how traders operate and execute trades in the crypto market. After that, we participated in a hackathon and worked on designing an algorithmic trading bot using Python, React.js, and PostgreSQL. | Crypto Trading Session & Hackathon Participation | Completed
2026-03-16
1 | Iworked on analyzing how the IGRS system can be implemented on blockchain platforms such as Hyperledger and Avalanche, and discussed the backend changes required for deployment. We also reviewed issues in the LC system related to data entry mismatches. To solve this, we discussed a solution where OCR-extracted data can be matched with real data before anchoring to ensure accuracy and consistency. | IGRS Blockchain Implementation Research & LC System Data Validation | Completed/Processing
2026-03-17
1 | I worked on adding QR functionality in the IGRS system, but it was later removed due to a new backend implementation by Jatin Sir. I also conducted research related to the Labour Department use case. In addition, I worked on fixing bugs and cleaning up code in JustifAI. After the Birsa Munda meeting, I implemented the discussed changes in the system. | IGRS QR Update, Bug Fixes & Labour Department Research | Completed/Processing
2026-03-18
1 | Yogesh Sir and I visited VNSU Surat to present the JustifAI demo, showcasing the system features, workflow, and verification process. | JustifAI Demo Presentation – VNSU Surat | Completed
2026-03-19
1 | we had the new office puja. After that, I reviewed the Jalgaon tender and worked on preparing the technical proposal with the help of Jatin Sir. | Office Inauguration, Tender Review & Technical Proposal | Completed
2026-03-20
1 | I worked on implementing the resume builder feature. I also developed and improved the dual preview mode in JustifAI to enhance document viewing and verification experience. | Resume Builder Implementation & JustifAI Dual Preview Mode | Completed
2026-03-23
1 | I worked on converting the IGRS system to Hyperledger and integrated the frontend with the new Hyperledger-based backend. I also planned how SMP can be implemented on blockchain, including the overall approach and integration flow. | IGRS Hyperledger Integration & Blockchain Planning | Completed
2026-03-24
1 | I added 2000 records in JustifAI to test load balancing and measure system performance and response time. I also reviewed the IGRS chatbot and SMP blockchain APIs. In addition, I discussed improvements for the JustifAI student wallet, including light and dark theme support, with Nand. | Load Testing, API Review & UI Theme Discussion | Completed
2026-03-25
1 | I worked on improving the IGRS workflow and made updates in JustifAI. I also attended project meetings, worked on scripts, and added verification personnel data to the system to support the verification process. | IGRS Flow Enhancement, JustifAI Updates & Verification Data Integration | Completed
2026-03-26
1 | I worked on JustifAI development and coordinated activities for both the JadeLC and SMP projects to ensure smooth progress and alignment across tasks. | JustifAI Development & Project Coordination | Completed
2026-03-27
1 | in the morning, I worked on fixing some blockchain-related blockers in SMP. After that, I worked on the SMP live setup with Bhadresh Bhai and reviewed integrations with Port Chain and MPESB to ensure proper functionality. | SMP Blockchain Fixes & Live Deployment Review | Completed
2026-03-28
1 | we worked on defining and refining the product structure for both the IGRS system and the PortChain platform, focusing on overall architecture, module organization, and system flow. | IGRS & PortChain Product Structure Design | Completed
2026-03-31
1 | I worked on both the frontend and backend of the PortChain system and completed integration with the modules provided by Ritam and Soumjit to ensure smooth functionality. | PortChain Frontend & Backend Integration | Completed

## Feb 2026
Sr. No. | Task | Task type | Status
2026-02-02
1 | I worked on building the LC system and designing its overall structure and layout. | LC System Development & Design | Completed
2026-02-03
1 | I worked on improving the OCR system and implemented integration with the .NET ERP (GNC). I also updated the LC system by changing the ABIs and performed testing to ensure everything works correctly. | OCR Enhancement, .NET ERP (GNC) Integration & LC System ABI Update | Completed
2026-02-04
1 | I worked on redesigning the LC system and refined the layout and structure to make it more polished, clear, and user friendly. | LC System Redesign | Completed
2026-02-05
1 | I worked on improving several system features to make them more robust and reliable, and updated the code accordingly. | System Enhancement & Code Updates | Completed
2026-02-06
1 | I worked on enhancing the VD system and optimized PDF handling by removing Base64 storage and avoiding the use of storage libraries for saving PDFs. This improves performance and reduces storage overhead. | VD System Enhancement & PDF Storage Optimization | Completed
2026-02-09
1 | I worked on testing and evaluating the OCR system. The results were partially successful, but accuracy and reliability need further improvement, which will be addressed in the next iteration. | OCR Testing & Evaluation | Processing
2026-02-10
1 | I improved the system by implementing a new grid-based layout for better structure and usability. I also integrated Google OCR API to enhance text recognition accuracy and overall system performance. | Grid Layout Enhancement & Google OCR Integration | Completed but Failed
2026-02-11
1 | I collected the required data and presented the LC system demo in Junagadh. The session focused on explaining the workflow, verification process, and overall system functionality. | Data Collection & LC Demo Presentation | Completed
2026-02-12
1 | I worked with the data provided by Nobel University and performed testing to ensure system reliability. I also made improvements to standardize and strengthen access points so the system can work consistently for all universities. | University Data Testing & Access Standardization | Completed
2026-02-13
1 | I worked on designing the storage system for the second project of Nobel School. I analyzed how the idea can be implemented practically, reviewed possible approaches, and evaluated how it can integrate with the existing system architecture. | Storage System Planning – Nobel School Project | Completed
2026-02-16
1 | we worked on improving the OCR system. However, we faced issues with accuracy on some images. Based on this, we decided to implement a fallback approach where, in case of OCR failure or invalid results, a preview will be shown so that the verifier can manually check and visually confirm the document. | OCR Testing & Manual Verification Flow Update | Completed
2 | I shared the updated code with Jatin Sir for the live demo purpose. After that, I continued working on OCR testing and improvements. | Live Demo Code Sharing & OCR Testing | Completed
2026-02-17
1 | I worked on the IGRS frontend, focusing on implementing and refining the user interface and ensuring proper integration with the existing system functionality. | IGRS Frontend Development | Completed
2026-02-18
1 | I worked on both the IGRS frontend and backend. I implemented required features, handled integration between frontend and backend, and ensured proper functionality across the system. | IGRS Frontend & Backend Development | Completed
2026-02-19
1 | I worked on implementing blockchain-based certificate generation and continued development work on the IGRS system, focusing on integration and functionality improvements. | Blockchain Certificate Generation & IGRS Development | Completed
2026-02-20
1 | I worked on implementing the preview display for certificates in case of invalid verification. This ensures that when a certificate is marked invalid, a proper preview is shown for review and clarity. | Invalid Certificate Preview Handling | Completed
2026-02-23
1 | I tested the certificate verification system to ensure proper functionality and accuracy. I also worked on understanding the IGRS workflow in detail and added Jantri integration as part of the system enhancements. | Certificate Testing, IGRS Analysis & Jantri Integration | Completed
2026-02-24
1 | I worked on the certificate project and improved the QR system by implementing accurate QR placement and multi-QR detection. I also refined the certificate templates to ensure proper alignment and professional formatting. In addition, I implemented several advanced enhancements to improve overall verification accuracy and system performance. | Certificate Project Enhancement – QR & Template Improvements | Completed
2026-02-25
1 | we prepared and finalized the IGRS demo for proper presentation and testing. We also integrated blockchain-based certificates into the student wallet and implemented multi-language support in the certificate templates to improve accessibility and usability. | IGRS Demo, Student Wallet Integration & Multi-Language Templates | Completed
2026-02-26
1 | we worked on implementing a new design in Justifai and integrated it into the existing system to ensure smooth functionality and consistency across modules. | Justifai UI Redesign & Integration | Completed
2026-02-27
1 | I visited Jalgaon to present the system demo. The session focused on explaining the workflow, features, and overall functionality of the platform. | Demo Presentation – Jalgaon | Completed

## January 2026
Sr. No. | Task | Task type | Status
2026-01-01
1 | I worked on updating the QR verification system so that, at scan time, the preview is shown directly without fetching data from the database. | QR Scan Preview | Completed
2 | I also worked on QR code design improvements and visual enhancements | Design Enhancement | Process
2026-01-02
1 | I worked on implementing and testing the canonicalization system and integrated it into our product workflow. The changes were tested to ensure consistent data handling and correct behavior across the system. | Canonicalization System Implementation & Testing | Completed
2026-01-05
1 | I implemented changes in the ERP and SDK modules and updated the webhook configurations to support the new workflow. The updates were tested to ensure proper integration and reliable data flow across the system. | ERP & SDK Updates with Webhook Enhancements | Completed
2026-01-06
1 | I worked on the ERP system and thoroughly checked the SDK. I also reviewed our existing product and made updates to the smart contract ABIs to align with the latest changes and ensure proper integration. | ERP & SDK Review with ABI Updates | Completed
2026-01-07
1 | I updated the smart contract ABI integration in both the backend and frontend. I also modified and improved the OCR system using Python to enhance accuracy and processing reliability. | ABI Updates & OCR System Enhancement | Completed
2026-01-08
1 | I updated the smart contract ABIs, implemented a new OTP feature, and added an improved log design to support better tracking and monitoring across the system. | ABI Updates, OTP Feature Implementation & Log Design Enhancement | Completed
2026-01-09
1 | I updated the verification code to improve accuracy and reliability. I also made changes to the Paddle OCR system to enhance text extraction and overall OCR performance. | Verification Logic Update & Paddle OCR System Enhancement | Completed
2026-01-12
1 | I integrated a new OCR library, made updates to the verification page, and performed checks on the ERP system to ensure everything works correctly with the latest changes. | OCR Library Integration, Verification Page Updates & ERP Review | Completed
2026-01-13
1 | I worked on the QR verification system to correctly display clear printed results for valid and invalid verification statuses. I also updated the blockchain proof display to improve clarity and accuracy during verification. | QR Verification System Update & Blockchain Proof Display Enhancement | Completed
2026-01-19
1 | I worked on updating the user management system and added email functionality to support notifications and related system workflows. | User Management Update & Email Functionality Integration | Completed
2026-01-20
1 | I tested the SDK, applied required updates, and successfully published the updated SDK for use. | SDK Testing, Update & Release | Completed
2026-01-21
1 | I worked on the redevelopment of the tenant model to improve structure, scalability, and integration with existing system components. | Tenant Model Redevelopment | Processing
2026-01-22
1 | I updated the tenant model and implemented access assignment to ensure proper permission control and role-based access within the system. | Tenant Model Update & Access Assignment | Processing
2026-01-27
1 | I worked on the tenant management system and completed the required updates. I also implemented and finalized the webhook functionality. Both tasks are completed successfully. | Tenant Management System & Webhook Integration | Completed
2026-01-28
1 | I worked on the live JustifAI system and resolve code errors and layout issues | Live System | Processing
2026-01-29
1 | I worked on the live system and made updates to the verification layout. I also implemented changes in the SDK and fixed related code issues to ensure better stability and functionality. | Verification Layout & SDK Changes | Completed

## December 2025
Sr. No. | Task | Task type | Status
2025-12-18
1 | Worked on integrating the blockchain ABI into the project and researched methods to embed the verification page into external websites. Completed updates to the verification page and modified the verification function logic and algorithm to improve validation accuracy. | Blockchain Integration & Verification Enhancement | Completed
2025-12-19
1 | Worked on updating and improving the verification page layout for better clarity and usability. Along with this, I will research methods to detect whether a verified PDF has been scanned or copied. After the research, I will develop a demo implementation to identify scanned or copied PDFs using OCR-based techniques. | Verification System Enhancement & Research | Completed
2025-12-22
1 | I resolved warnings and errors related to ED, EI, and SI. I also updated the hashing algorithm from SHA-256 to Keccak-256 to enhance the security of PDF verification. Additionally, the updated code has been pushed to GitHub. | Verification System Enhancement & Research | Completed
2025-12-23
1 | updated the hashing algorithm from SHA-256 to Keccak-256 for stronger PDF security, pushed all updated code to GitHub, tested temporary PDF handling in the system, and verified new API features including client PDF upload and JSON file upload. | Verification System Enhancement & API Integration | Completed
2025-12-24
1 | I worked on the Client PDF Upload System and implemented the required code changes. I have successfully pushed the updated code to GitHub. Currently, there is a mismatch issue with the SI verification time, which I will resolve tomorrow. | Verification System Enhancement & API Integration | Completed
2025-12-25
1 | I worked on implementing the client-side PDF upload flow to ensure the VD is properly embedded and verified accurately. I also developed and configured webhook URLs for all three features: CSV upload, JSON upload, and direct PDF upload. After implementation, I tested all related APIs to confirm correct functionality | Client Upload, Verification & Webhook Integration | Completed
2 | I worked on QR code enhancement | Qr Code Verification | Completed
2025-12-26
1 | I tested multiple QR codes to understand their behavior and different use cases, including how they store and redirect data during verification. I also researched how QR codes work internally, how they are generated, and how they can be used securely in document and certificate verification systems. The focus was on understanding practical implementation details and identifying best practices for reliable QR-based validation | QR Code Analysis & Verification Research | Completed
2025-12-29
1 | I worked on the QR verification system and tested multiple QR code scenarios to understand their behavior and verification flow. I also completed the implementation to properly detect and handle PDFs that are modified using append-based software, ensuring correct tamper validation. | QR Code Analysis & Verification Research | Completed
2 | I created five different templates for testing the system. Work on these test templates is currently in progress. | PDF Integrity Validation | Process
2025-12-30
1 | Completed the zip verification logic to ensure accurate validation of all documents inside the archive. Fixed QR code positioning based on certificate templates to maintain consistent scanning and verification. In parallel, researched real-world QR verification systems such as FSSAI and ISO to understand how their QR codes are generated, positioned, and verified, and analyzed how those approaches can be applied to improve our system. | Verification System Enhancement & Research | Completed
2025-12-31
1 | I worked on enhancing the QR verification system. I implemented Java-based code to store image data within the QR code and tested its behavior during verification. Along with development work, I researched how offline QR verification works and analyzed different approaches used for successful verification without internet connectivity. | QR Verification System Development & Research | Completed
2 | I created a demo implementation within the Java project to validate the feasibility and accuracy of the offline QR verification flow |  | Completed